Il Ngwesi Biodiversity Project – Field Report September 2023

Table of Contents

- Il Ngwesi Community Conservancy and Il Ngwesi Biodiversity Project

- Our Mission and Vision

- A note about the Invitation from the Chair - Kip Ole Polos, and Edwin Kisio - Il Ngwesi’s Conservation Manager

- A short overview about our visit, the work achieved and outputs

- Research Question

- Methodology

- Logistics

- Cultural Knowledge and Lay Science Booklet

- Key findings and short summary of the plan forward to 2024

- Appendix 1: Team Photograph and profiles of the Il Ngwesi Biodiversity Project core team

- Appendix 2: Summary of daily activities

- Appendix 3: Maps of Il Ngwesi

- Appendix 4: Species Lists

  - Mammal List

  - Bird List

  - Grass List

- Appendix 5: Laikipiak Maa Glossary

- Bibliography

- Acknowledgements

- Key contacts and address in Kenya and UK

This is an internal working document summarising the outcomes of the 2023 Phase 1 reconnaissance trip to Il Ngwesi, which lasted two weeks, and outlining plans for the 2024 Phase 2 survey. This report is aimed at project members, supporters and other interested parties.  This document focuses primarily on Phase 1, and more detailed documents are being compiled which outline plans for Phase 2, including methodology and budgeting.

# Il Ngwesi Community Conservancy and Il Ngwesi Biodiversity Project

Il Ngwesi Community Conservancy claims the title of Africa’s first-ever community-owned lodge, founded in 1995 and well-ahead of its game in the conservation scene. Spanning 22,000 acres of rocky scarps and wooded valleys dropping from the iconic Laikipia plateau to the rolling savanna plains along the Ngare Ndare river, Il Ngwesi is an entirely indigenous owned and managed entity run by the local Laikipiak Maasai community. In the Laikipiak Maa language, Il Ngwesi means “People of Wildlife”. We are committed to having a Maa name for our special project, representing what we stand for in Il Ngwesi’s own language. While we previously decided on Oramat, we recently realised that other organisations have used this term, and it does not fully capture what our project is about. Our Maasai teammates have suggested “Enkirrita”, which conveys the sense of looking after, protecting and conserving something. Until we finalise the Maa name, we are for now the Il Ngwesi Biodiversity Project; perhaps soon we shall be the Enkirrita Il Ngwesi Biodiversity Project! Please bear with us and watch this exciting space.

Left: Looking out over Il Ngwesi. Right: Rain clouds over neighbouring Lewa Wildlife Conservancy.

Photos: Barbara Francik

The conservancy has won an accolade of awards throughout its lifetime, including the prestigious United Nations Equator Prize in 2004, a finalist for Best Community Safari Property in Africa in the 2011 Safari Guide, and silver-rated for sustainable tourism by Ecotourism Kenya from 2013-2015. More recently in 2022, Il Ngwesi won Ecotourism Kenya’s prestigious Eco Warrior Award for Best Community Tourism Initiative. The eco-lodge itself is one of the most exemplary examples of deadwood architecture in the world, opened in 1996 and catering to a high-end eco-tourism market. The lodge has stimulated the development of many other conservation enterprises including cultural villages, artisanal handicraft production based on the Maasai’s famous saen (beads), and community-run campsites. The revenues generated by these initiatives have been reinvested in infrastructure projects prioritised by the Maasai community at annual general meetings. These include water infrastructure projects, schools, educational scholarships, and extensive health outreach services.

Established as an alternative venture to improve community livelihoods through wildlife conservation, Il Ngwesi’s vision is to integrate community development, economic benefit and a sustainable environment with biodiversity conservation. Since its inception, Il Ngwesi has been in a close and constant partnership with Lewa Wildlife Conservancy, a UNESCO world heritage site directly bordering the conservancy. Approximately 80% of Il Ngwesi’s land area is dedicated to conservation, split between a core conservation area and a network of grazing blocks used for rotational livestock grazing in the dry season, ensuring the survival of Maasai pastoralist culture. During the wet season, livestock are kept within the two settlement zones on the outskirts of the conservancy where the local communities live.

Il Ngwesi is home to many species of key conservation concern, including white rhino (Ceratotherium simium), African elephants (Loxodonta africana ), lions (Panthera leo), Grevy’s zebra (Equus grevyi), leopards (Panthera pardus), reticulated giraffe (Giraffa reticulata) and the critically endangered pancake tortoise (Malacochersus tornieri). The conservancy boasts an amazing array of birds, from the superb starling (Lamprotornis superbus) and D’Arnaud’s barbet (Trachyphonus darnaudii) and Von der Decken Hornbill, the inspiration for Zazu from the Lion King, through to larger species including the Somali ostrich, white-backed vultures (Gyps africanus), Rüppell’s vulture (Gyps rueppellii) and lappet-faced vultures (Torgos tracheliotos). During the wet season, Il Ngwesi’s wildlife truly springs to life, hosting thousands of elephants that seasonally migrate to these abundant lands, along with an explosion of lush grass, flowers and millions of insects that underpin this amazing ecosystem. Il Ngwesi forms a vital lifeline and corridor in a wider conservation network stretching across Kenya’s Northern Rangelands, including conservancies such as Lewa, Borana, Leparua, Lekurruki and other areas critical for both wildlife and people, such as the Mukogodo Forest.

Kenya’s community conservation programmes are amongst the world’s most highly-regarded. Now, 28 years after Il Ngwesi began its conservation journey, we have an invaluable opportunity to quantify the achievements and impact of this bold conservation success story. Being the first community-owned lodge and conservation area in Africa, our mission is to understand the dividends paid through the conservation actions taken here.

Our Mission and Vision

Our core team at the Il Ngwesi Biodiversity Project (IBP) is a cross-cutting Kenyan-UK team, made up of Maasai warriors, rangers and scientists alongside early-career conservationists and scholars from Durham and Oxford Universities (See Appendix 1).

Our mission is to systematically categorise Il Ngwesi’s biodiversity, quantifying the differences between Il Ngwesi’s core conservation area, grazing blocks, and settlements. This will provide information useful to land management plans, contributing to the conservancy’s vision of fostering biodiversity conservation, sustainable development, and the flourishing of Maasai culture hand-in-hand.

This mission is intended to take place in 2024, with a wet season survey ideally at the end of May and a dry season survey in August/September. Our vision is for this survey to be an initial thrust towards creating Il Ngwesi’s own long-term science programme and a research camp where scientists from the local community and the world over can come to learn from and study Il Ngwesi’s stunning biodiversity. Il Ngwesi is a role model in the community conservancy model, with neighbouring conservancies visiting and learning from their actions. Our hope is to extend this learning to the scientific and conservation realm, contributing to a vision of a flourishing Northern Rangelands.

Read on to find out about our project, team and the results of our Phase One 2023 mission!

# A note about the Invitation from the Chairman – Kip Ole Polos and Il Ngwesi’s Conservation Manager – Edwin Kisio

We are very grateful to have received letters of invitation from Il Ngwesi Community Conservancy (see below) in order to undertake this initial phase of the project. We thank Edwin Kisio, our conservation manager, along with the other members of Il Ngwesi’s board for their warmth, hospitality and openness to developing this biodiversity project, as envisioned by Chairman Kip Ole Polos.

# A short overview about our visit, the work achieved and outputs

This Phase One visit had six key goals:

1)	Ensure that the planned biodiversity study truly addresses Il Ngwesi’s conservation objectives and benefits the local Maasai community.

2)	To familiarise the team in the methodologies we will use in our long-term project culminating in a multi-month biodiversity survey and mapping mission in 2024 (1-2 months in the wet and dry seasons, respectively).

3)	To start the process of compiling a lay science booklet of biodiversity and local/traditional knowledge from Il Ngwesi (including medicinal plants, mammal list, etc.).

4)	To inform precise locations for the major survey through familiarisation of the local geography.

5)	To deepen our understanding of necessary logistics for our major survey.

6)	To co-produce a glossary of the unique Laikipiak Maa dialect containing words and phrases important both in the lives of the people of Il Ngwesi, and that which Laikipiak Maa learners would benefit from knowing!

We are absolutely delighted to announce that we accomplished every single one of these goals and more!

Research Question

For our 2024 research, our research question is (roughly!):

“How does biodiversity differ across Il Ngwesi, with reference to land management (core conservation area, grazing blocks and settlements), habitat type, geology and hydrology?”

Supporting Objectives:

- Produce a detailed biodiversity report for Il Ngwesi. The report will include an assessment of species’ presence and, where possible, species abundance and temporal population trends. It will include an analysis of the differences in biodiversity between different grazing and conservation blocks.

- Produce a detailed habitat map of the Conservancy, including local place names.

- Develop a training programme for all members of the survey, with a focus on sampling techniques, GIS field mapping, and data analysis for longer-term monitoring of the Conservancy. This will allow skills to be passed down to future teams and enable a long-term surveying effort.

- Outreach via a written/recorded expedition journal produced jointly by the Kenya-UK team.

- Produce a joint Kenya-UK academic publication to share the results of the survey.

- Produce an open-access glossary of Laikipiak Maa words and phrases.

- Document local knowledge, history, traditions, and stories.

- Produce a lay science and culture booklet which will introduce the local community and visitors to the people and work of the Conservancy. The booklet will include a record of the expedition, species lists, and key findings. The booklet will also include local knowledge, traditions, history, stories, and a glossary of Laikipiak Maa words and phrases.

The findings of this project will help inform the development of Il Ngwesi’s rotational grazing system. The system relies on the periodic movement of cattle between different grazing blocks (see maps), allowing land to recover from grazing pressure. The system allows traditional Maasai pastoralist culture to flourish in a landscape which is ecologically diverse and valuable. This project will provide an impact assessment of the rotational grazing strategy, analysing its effects on biodiversity and its effectiveness as a conservation strategy.

Given that this is Il Ngwesi’s first self-driven research, we hope to generate crucial baseline biodiversity data. For this reason, we are planning to study a wide range of organisms including insects, plants (grasses, shrubs and trees), birds, mammals and reptiles where possible. As biodiversity is a core component of Il Ngwesi’s value proposition as one of Kenya’s top eco-lodges and community conservancies, we believe that quantifying the conservation impact of their land management practices will be of benefit to inform land management in the aim of further optimising Il Ngwesi’s conservation and sustainable development actions.

Our research question has been guided by conversations with Il Ngwesi’s Conservation Manager Edwin Kisio, and many other experts including Ian Craig of Lewa Wildlife Conservancy and Mohammad Shibia of the Northern Rangeland Trust, hence we are confident that we are addressing a question that benefits Il Ngwesi.

Methodology

A crucial element of this reconnaissance trip was the testing of methods proposed for use in the 2024 survey. The variety of habits at Il Ngwesi means that not all methods are appropriate in all situations, and matters such as accessibility of surveying sites and man-power will affect which methods can realistically be deployed in 2024. We are now confident that we have a good understanding of the applicability of different methods in different areas of Il Ngwesi, and have a clearer picture of the logistics involved in employing them. The testing of methods was also a key opportunity for team members to familiarise themselves with previously unencountered methods and share knowledge and previous experience.

The methods tested, which we plan to use in 2024, are listed below:

-   	Sweep netting (insects) - Vigorous sweeping of a net through grass along a transect.

-   	Pitfall traps (insects, arthropods, reptiles) - A cup sunk into the ground, flush with the surface, targeting crawling arthropods such as beetles, spiders and scorpions, which fall into the trap.

-   	Point counts (birds and large mammals) - Remaining in a fixed location for 5-30 minutes and recording any animals observed/heard, and their distance from the surveying point.

-   	Line transects (bird survey) - Moving along a transect line and recording any birds observed/heard and their distance from the transect line.

-   	Belt transects and quadrats (insects and plants) - Moving along a transect line and placing quadrats at intervals along the line. Identifying and counting all insect and grass species within each quadrat.

-   	Tree beating (insects) - Holding a white sheet under a tree/bush/shrub and beating the plant vigorously to dislodge insects onto the sheet, where they can be easily observed and collected.

-   	Tick drags (ticks) - Dragging a large sheet of heavy, wide cloth through grass and examining it for ticks.

-   	Camera trapping (large mammals) - Remote motion-activated cameras set up around wildlife hotspots, such as watering holes. Especially effective for difficult to observe, nocturnal species.

-   	Pan traps (insects) - Coloured pans filled with water, dishwashing liquid (to break the surface tension) and a preservative (e.g. ethanol). Insects are attracted to the bright colours and sink into the preservative solution.

-   	Flight intercept traps (insects) -  A transparent sheet of plastic/netting strung across an insect flyway (e.g. a gap between trees) with trays of preservative solution at the bottom. Flying insects collide with the sheet and fall into the collecting trays.

-   	Moth traps (insects) - A high UV bulb over a box designed like a lobster pot. Moths are attracted to the light and funnelled into the box, where they can be collected the next morning.

-     Mammal ink footprint tunnels (small mammals) - a small bait (peanut butter) is placed inside a small plastic tunnel with paper and ink pads on either side. When small mammals come to feed on the bait, they step in the ink and leave behind paw-prints on the paper. Whilst this method will not provide species-level identifications for most small mammals, it can support identifications on a higher taxonomic level.

-   	Grass identification - Visual identification of grass species.

Species Lists are in the process of being compiled for mammals, birds, insects and grasses (see bibliography). All of these lists are works in progress and will be expanded as species are observed and recorded. The lists are based on observations made during the two-week reconnaissance trip and/or local knowledge of Il Ngwesi’s flora and fauna. In the case of the mammals list, note that some of the smaller species have been included based on their known geographic ranges, rather than due to specific observations or knowledge of their presence in Il Ngwesi - where this is the case, it has been noted on the species list. The current insect list is not yet at species level because identification of insects to species level is a complex process requiring the input of specialists and experts. Thus, insects have so far been categorised by order. Species level identifications will be included in the 2024 surveys.

Besides recording species presence, we are also aiming to include Maasai names for each species, where possible, and we are in the process of compiling these.

Proposed  Methodology for 2024

The main aim for 2024 is to establish species presence, and abundance where possible, to build a species list for Il Ngwesi. This list will be split between grazing blocks and habitat types, in order to allow us to compare the effects of different management regimes on biodiversity and thus inform future management and conservation plans. We also aim to produce a detailed habitat map of Il Ngwesi using GIS.

Research Plots

For the full 2024 survey, the conservancy will be split into plots within which the above methods will be carried out. We hope to use existing plots developed for the purposes of Veg-CoMM surveys run by the Northern Rangelands Trust, which are spread across the geographic range of Il Ngwesi and cover its different habitat types. This will allow us to build on existing data on vegetation diversity and cover and link it to our measures of biodiversity. An additional benefit of using the Veg-CoMMs plots is that they form part of a landscape-wide carbon auditing programme, into which our data can feed. Within each plot, subplots will be created following the methodology outlined in the Land Degradation Surveillance Framework (LDSF) Field Manual developed by Tor-G. Vågen and Leigh Ann Winowiecki.

The exact selection of methodologies deployed in each plot will depend on the habitat type and accessibility of each area to be surveyed. For example, flight intercepts may be impractical in very open habitats, so may be replaced by pan traps. Additionally, the use of lethal and indiscriminate traps will be limited to avoid over-sampling and they will not be used in all plots.

More information on Veg-CoMMs: https://www.nrt-kenya.org/rangelands

More information on the LDSF manual: https://worldagroforestry.org/output/land-degradation-surveillance-framework-field-manual

An extract from the LDSF manual, demonstrating plots and subplots.

Sampling and Species Identification

Target insect taxa will be collected and preserved in ethanol in order to conserve DNA. Although DNA analysis is currently beyond the scope of this project, it will establish a valuable source of data for future researchers. For some distinct taxa, e.g. several members of the Lepidoptera and Odonata, photographic records will for the most part be sufficient to give accurate species identification without the need to take samples. We are in contact with the National Museums of Kenya and aim to collaborate with experts in Kenya in order to identify the species we find.

Birds, mammals and reptiles will be identified in the field or from photographic records. They will not be sampled directly. In the case of birds, and possibly large mammals, remote acoustic monitoring is a possibility. This method would allow us to collect large amounts of data on species presence with limited man-power in the field, which could make it a useful option for long-term sampling beyond the planned two-month survey.

Plant specimens will be collected and pressed in order to start building up a reference collection for Il Ngwesi which will provide a ready source of specimens to support future research. This will allow plants to be more readily identified in the field.

The team setting a moth trap, waking up early the next morning to discover a treasure trove of moths!

Photo: Barbara Francik

Top to bottom, left to right: Red billed hornbills, Superb starling, White rhinos, Spotted hyena, Vervet monkey, Grevy’s zebra, Kori bustard (Photos: Barbara Francik)

Top to bottom, left to right: Red billed hornbills, Superb starling, White rhinos, Spotted hyena, Vervet monkey, Grevy’s zebra, Kori bustard (Photos: Barbara Francik)

Top to bottom, left to right: Scorpion, Jumping spider, Scorpion glowing under UV light, Pseudoscorpion, Spider, Mantis, Giant millipede, Stick insect, Longhorn beetle, Throthing tiger moth, Cricket.

Photos: Barbara Francik

Top to bottom, left to right: Scorpion, Jumping spider, Scorpion glowing under UV light, Pseudoscorpion, Spider, Mantis, Giant millipede, Stick insect, Longhorn beetle, Throthing tiger moth, Cricket.

Photos: Barbara Francik

Logistics

Phase one had taught the team a great deal about the necessary logistics required for our plans and we thank everyone we have met who has provided vital information that will shape the logistical challenge we face ahead in setting up a research camp and biodiversity survey for 2024.

We are currently working out the final details of our 2024 budget and this will be made available shortly, along with a breakdown of our 2023 budgeting.

Local Partners

Forming connections and building collaborations with local organisations and initiatives will be key to the success of this project. A wealth of expertise, experience, existing data, established protocols, and conservation programmes exist in the area. We want to ensure that our project feeds into the bigger, landscape-level picture and that the data we collect will feed into wider initiatives. Through local collaborations, we hope to ensure that the Il Ngwesi project continues into the long-term, beyond the 2024 survey, and continues to produce data valuable to Il Ngwesi and partner organisations. We were privileged to be able to meet with a wide variety of people and organisations during Phase 1, and we hope to continue working with them into the future. Some of the people and institutions we met include:

- Lewa Wildlife Conservancy

- Mpala Research Centre

- Northern Rangelands Trust representatives

- Natural State

- World Agroforestry Institute (Nairobi)

- Dr. Dino Martins (Chief Executive Officer of the Turkana Basin Institute)

- Steve Collins (Founder of the African Butterfly Research Institute)

Cultural Knowledge and Lay Science Booklet

The aim of the lay science booklet is to give the local community, visitors to Il Ngwesi, and other interested parties an insight into the conservation and cultural work of the Conservancy. It will include information on Il Ngwesi’s various conservation and community development schemes. It will also include an overview of Il Ngwesi’s biodiversity based on our surveys, including species checklists which will hopefully encourage people to add their own observations to Il Ngwesi’s growing knowledge bank. The booklet will also include a glossary of Laikipiak Maa words and phrases, traditional knowledge, and local stories. The aim is to help document these aspects of Maasai culture, and educate people from outside Il Ngwesi on the history and practices of the Laikipiak Maasai people. We aim to make the booklet accessible to as many people as possible and thus hope to produce it in Maasai, Swahili and English.

During Phase 1, we have begun to compile a glossary of Laikipiak Maa words and phrases, which will be included in the lay science booklet. We have also started to build species lists, based on observations made during Phase 1, and local knowledge of Il Ngwesi’s flora and fauna.

Some of the people the team was lucky enough to meet with. From top left clockwise: Dr Tor-Gunnar Vågen of ICRAF/World Agroforestry; Steve Collins of the African Butterfly Research Institute; John Tanui from Lewa Wildlife Conservancy and Kasaine Ietiktik from the Northern Rangelands Trust, featuring Il Ngwesi Conservation Manager Edwin Kisio; Jonathan Baillie, Founder and CEO of Natural State; Mohammad Shibia and Tarry Boru from the Northern Rangelands Trust; Ian Craig, founder of Lewa Wildlife Conservancy and Chief of Conservation and Development for the Northern Rangelands Trust.

# Key findings and short summary of the plan forward to 2024

The work we carried out this year will set a solid foundation for the 2024 surveys and hopefully for the continuation of this project by Il Ngwesi well into the future. We have established a research question, confirmed that our proposed methods will be suitable for the habitats of Il Ngwesi, become familiar with the layout of the Conservancy, met with the local team and local partners, and learned a huge amount about Maasai culture. We have also started to compile species lists based on what we have observed so far and the knowledge of people at Il Ngwesi, which will serve as a key aid in identifying species next year.

Going forwards, we will work closely, both within the team and with our stakeholders and potential partners, to achieve our larger mission and vision as stated earlier in this report.

Our chief goals going forward are:

1)	Acquiring all relevant research permits necessary for next year

2)	Successfully fundraising enough money to make this project a reality – our budget is still under construction but given that this 2-week Phase One cost approximately £11,000, Ian Craig suggested a rough figure of £50,000, which he believes is certainly achievable.

3)	Developing our partnerships and understanding the nature of each relationship in order to maximise benefit for all parties, e.g. with the Northern Rangelands Trust, Natural State, National Museums of Kenya.

4)	Further refining our research methodology to ensure we meet our research question in an achievable and scientifically robust manner

5)	Acquiring equipment for the project and setting up a research camp at Il Ngwesi to serve as our base of operations, including space for visiting researchers and project partners to visit and knowledge-exchange with our team.

African savanna elephants (Loxodonta africana). (Photo:Jamie Bolam)

# Appendix 1: Team Photograph and profiles of the Il Ngwesi Biodiversity Project core team

The Il Ngwesi Biodiversity Project founding core members. From left to right: Eva Rundle, Everlyne Masikonte, Jamie Bolam, Benjamin Ngila, Robin Tentuan, Barbara Francik, Cyrus Kisio, Francis McAdie.

Cyrus Kisio and Francis McAdie – Kenyan and UK Team Leads

Cyrus: I am Cyrus Nkoyo kisio from Ilngwesi Conservancy, a lover of wildlife and their habitat. My role in the team is leading the Kenyan half and working closely together with Francis and our UK counterparts.

Francis: I am a final-year BSc Biology student from Durham University, specialising in ecology and conservation. I am the UK team lead, ensuring we continue making progress on this important project and liaising closely with Cyrus and our Conservation Manager Edwin Kisio. I am a proud member of the Royal Geographic Society, without whom this project would not have existed.

Eva Rundle (Eva with an A) – Fundraising and Outreach

Everlyne Masikonte (Eva with an E) – Fundraising and Outreach

Eva with an A: I have just graduated with a BSc in Natural Sciences from Durham University. My role, alongside my fellow Eva, is to be the focus point of the team regarding finances, grant applications, budgeting and social media.

Eva with an E: I am a Maasai, born and raised in Laikipia county. I have graduated from with a BSc in Livestock Improvement. For the past two years have been working with the Northern Rangelands Trust on cattle and rangeland management. There, I developed my passion for conservation and I hope to further my studies. I do budgeting and social media for the team.

Benjamin Ngila – Team Artist

Barbara Francik – Chief methodologist and Team Artist

Benjamin: I am a moran (Maasai warrior) and live in the Mukugodo Forest to the west of Il Ngwesi. My role in the team is to produce artwork to support our vision and outreach, and I have in-depth knowledge of Il Ngwesi’s biodiversity and ecology, able to interpret wildlife signs, identify plants, birds and more, and understand their traditional roles and uses in our Maasai way of life. My father is a medicine man and has taught me much about the uses of the plants that surround us.

Barbara: I am a master’s student at the University of Oxford currently studying Biology. As chief methodologist for the team, I guide our team in choosing and trialling effective biodiversity surveying techniques, ensuring our project has a robust scientific underpinning! I have previously worked on biodiversity surveying and animal behaviour, both vertebrates and invertebrates. I am studying Manx Shearwaters for my master’s research.

Jamie Bolam – GIS Specialist and Secretary

Robin Tentuan – GIS Specialist and Secretary

Jamie: I am an early-career conservationist and recently completed my MSc in Biodiversity, Conservation and Management at the University of Oxford and a proud member of St Cross College. As one of the teams’ GIS specialists, I use geospatial data to benefit our project, for example making accurate and informative maps! I am also a team secretary, taking notes during meetings and ensuring the team follows on our action points. Beyond this, I help wherever necessary. I have a passion for languages and have been helping find and create resources for the UK team in learning Kiswahili and Maa, aided by our wonderful Kenyan counterparts!

Robin: I am a moran (Maasai warrior) from the Ngare Ndare Forest to the south of Il Ngwesi Community Conservancy and Lewa Wildlife Conservancy. I am studying a BSc in Botany and Zoology in Kenyatta University, Nairobi, having just completed my first year. My role in the team is to become our Kenyan GIS specialist, employing geospatial data to guide and inform our project. As one of the team’s secretaries alongside Jamie, I also take notes during our meetings and help out where needed! I will also serve as our key contact in Nairobi, liaising with our potential partners such as World Agroforestry and the African Butterfly Research Institute.

Appendix 2: Summary of daily activities

|  | am | lunch | pm | evening |
| --- | --- | --- | --- | --- |
| 29th August Tuesday | Flight to Kenya 10:10 am | Francis fly into Nairobi 14:45 | Rest of UK team flies in, arrives at 8:50pm | Stay with Steve Collins |
| 30th Aug Wednesday |  | Aims for day: - Sim cards - Hardware store - Team meeting - Other | Meeting with Dino Martins | Dinner with Steve Collins and Dino Martins |
| 31th Aug Thursday | Drive to Nanyuki, the UK team meets Cyrus | Drive to Mpala to pick up the Durham University equipment | Transfer to Il Ngwesi | Team daily roundup |
| 1st September Friday | Introductions with all team members present and kit demonstration Set up moth trap | Collection of maps and books from office | Game Drive around Il Ngwesi | Il Team daily roundup Moth trap |
| 2nd Sept Saturday | Health and safety meeting for team Aim to get idea of where we want to go | Francis and Cyrus collect maps and Methodology meeting with The Dudu Survey Team | Tour of Il Ngwesi to understand the lay of the land - from top of Escarpment down | Team daily roundup |
| 3rd Sept Sunday | Set up non lethal pitfall traps and sweep netting. Core area. | Make makeshift quadrat + tick drag | Quadrat insects Grass ID Combine with Camera trap relocation. Core Area | Flesh out agenda for meeting with for Ian Craig |
| 4th Sept Monday | 500m bird transect. Check pitfall traps. Core Area | Grass Identification | Insect quadrats, beat sheeting and tick drag. Block 3 | Bachata and Maasai dancing lessons. |
| 5th Sept Tuesday | Set up pan traps Play volleyball | Run through agenda for Ian with team | Set up 8 pitfall traps Block 3 Meeting with Ian Craig in Lewa. | Return to Il’Ngwesi |
| 6th Sept Wednesday | Drive to Isiolo to fuel up the car. Drive to Lewa to be guided through the JOCC by John Tanui, who will also introduce us to EarthRanger and Tableau software | Meet the GIS and WildlifeComs team to acquire Il Ngwesi data. | Check pitfall traps Block 3 Check pan traps and relocate camera traps. | Meeting with Edwin (Il Ngwesi conservancy manager) |
| 7th Sept Thursday | Drive to Mukogodo forest | Bird point survey Mukogodo forest | Preparing Agenda for Kieren, Mohamed and Jonathan | Team daily roundup |
| 8th Sept Friday | Meeting with Kieren about NKRCP Introduced to Lewa/NRT’s world famous tracking dogs | Meeting with Mohamed Shibia on NRT’s Rangeland managment. Lunch | Meeting with Jonathan Baille and the Natural state team. Drive back to Il Ngwesi | Team daily roundup |
| 9th Sept Saturday | Run through the results of the the meetings with Kieren, Mohamed and Natural state |  | Learning Maasai beading! Sundowner | Team daily roundup |
| 10th Sept Sunday | Flight intercept trap Lodge Mammal ink tunnels Lodge and Core Area | Start compiling PDF Document for Il Ngwesi Conservancy | Collecting camera traps | Team daily roundup |
| 11th Sept Monday | Collecting flight intercept traps and mammal ink tunnels Meeting with Nigel Winser online Large mammal point count with binoculars | Meeting in Isiolo with Edwin Kisio and Dominic Karmushu from the board to update on the team’s success together | Drive back to Il Ngwesi and down time - the team helps skin a goat for the night’s celebrations | Team farewell party - Nyama Choma, Maasai dancing and jumping competitions! |
| 12th Sept Tuesday | Second meeting with Natural state to discuss collaboration | Meeting with Ruwaydah & Faith to discuss marketing of our project B,E and J drive back to Nairobi. F drive Mpala |  | B, E and J stay with Steve Collins and F at Mpala |
| 13th Sept Wednesday | B, E and J go through meeting notes from the previous day | B, E and J meet Dr Tor-Gunnar Vågen of World Agroforestry in Nairobi to discuss collaboration | Travel to the airport | B,E and J home 22:45. F at Mpala. |

Appendix 3: Maps of Il Ngwesi

# 2023 Phase 1 Method Trialling Points

Satellite image of Il Ngwesi Community Conservancy, situated within Laikipia County, Kenya. Note the upland areas in the West of the Conservancy (darker green and marked by the 100m contour lines). Coloured points represent the locations where, in our 2023 Phase 1 mission, the Il Ngwesi Biodiversity Surveying Project trialled different biodiversity surveying methods for potential use in our 2024 mission.

# Grazing Blocks of Il Ngwesi

# Map of Il Ngwesi. Green = unregulated grazing, Blocks = regulated grazing, Core Area = Core conservation area and rhino boma.

A map of Il Ngwesi drawn by team artist Benjamin Ngila, including important locations in the conservancy and areas where the team trialled methodologies.

A map of Il Ngwesi drawn by team artist Benjamin Ngila, including important locations in the conservancy and areas where the team trialled methodologies.

Top: A map showing the outline of Il Ngwesi and neighbouring Mukugodo Forest (where Il Ngwesi’s people also live, e.g. Benjamin), and their position in Kenya.

Bottom: A 0.5km2 grid satellite map of Il Ngwesi.

Top: A map showing the outline of Il Ngwesi and neighbouring Mukugodo Forest (where Il Ngwesi’s people also live, e.g. Benjamin), and their position in Kenya.

Bottom: A 0.5km2 grid satellite map of Il Ngwesi.

Appendix 4: Species lists

The following species lists were compiled based on observations made during Phase 1 and local knowledge of Il Ngwesi’s flora and fauna. They are works in progress and will be extended as new species are recorded.

## Mammal list of Il’Ngwesi

NB: ? indicates that we are unsure as to the presence of these species, but based on their distribution they are possibly present. These could be future research opportunities.

| English name | Latin Name | Maa Name |
| --- | --- | --- |
| Afrotheria | Afrotheria |  |
| Hyraxes | Hyracoidea | enkinyanchur |
| Rock Hyrax * | Procavia johnstoni |  |
| Bush Hyrax * | Heterohyrax brucei |  |
| Proboscideans | Proboscidea |  |
| African Elephant * | Loxodonta africana | oltome |
| Sengis | Macroscelidea |  |
| Soft-furred sengi |  |  |
| Lesser sengi | Elephantulus sp. ? |  |
| Tubulidentates | Tubulidentata |  |
| Aardvark * | Orycteropus afer | naishiri dama |
| Primates | Primates |  |
| Olive Baboon * | Papio anubis | olotim |
| Vervet monkey * | Chlorocebus pygerythrus | oldere |
| Senegal galago | Galago senegalensis | orkima ong"u |
| Rodents | Rodentia |  |
| Old World Porcupines | Hystricidae |  |
| Crested porcupine * | Hystrix cristata | oiyai |
| Naked mole-rats | Heterocephalidae |  |
| Naked mole-rat | Heterocephalus glaber? | enderoni |
| Squirrels | Scuridae |  |
| Ochre bush squirrel * | Paraxerus ochraceus | parkobo |
| Unstriped ground squirrel * | Xerus rutilus |  |
| Dormice | Gliridae | enderoni |
| Graphiurus sp. | Graphiurus sp.? |  |
| Pouched rats/mice | Nesomyidae? | enderoni |
| Fat mice | Steatomys? | enderoni |
| African climbing mouse | Dendromus sp.? |  |
| Mice | Muridae |  |
| Brush-furred mice, | Lophuromys sp.? | enderoni |
| Spiny mice | Acomys sp.? |  |
| Gerbils | Gerbillinae |  |
| Gerbils | Gerbillus sp.? |  |
| Robust gerbils | Gerbilliscus sp.? |  |
| Slender gerbils | Taterillus sp.? |  |
| Rats and mice | Murinae | enderoni |
| Black rat | Rattus rattus? |  |
| Common mice | Mus sp.? |  |
| Multimammate rats | Mastomys sp.? |  |
| Groove-toothed rats | Otomys sp.? |  |
| Bush rats | Aethomys sp.? |  |
| Acacia rats | Thallomys sp.? |  |
| Grass rats | Arvicanthis sp.? |  |
| Lagomorphs | Lagomorpha |  |
| Leporidae |  |  |
| Cape hare | Lepus capensis | enkitejo |
| Scrub hare * | Lepus saxatillis |  |
| Hedgehogs | Erinaceinae |  |
| African hedgehogs * | Atelerix sp. | enjolis |
| Shrews | Soricomopha, Soricidae |  |
| White-toothed shrew | Corcidura sp.? | enderoni |
| Bats | Chiroptera | entipat |
| Fruit bats | Pteropodidae | entipat |
| Straw-coloured fruit bat | Eidolon helvum? |  |
| Egyptian rousette | Rousettus aegyptiacus? |  |
| Angola fruit bat | Lossonycteris angolensis? |  |
| Epauletted fruit bat | Epomophorus sp.? |  |
| Mouse-tailed bats | Rhinopomatidae | entipat |
| Mouse-tailed bats | Rhinopoma sp.? |  |
| Large-winged bats | Megadermatidae | entipat |
| Heart-nosed bat | Cardioderma cor? |  |
| Yellow-winged bat | Lavia frons? |  |
| Horseshoe bats, | Rhinolophidae | entipat |
| Horseshoe bats | Rhinilophus sp.? |  |
| Leaf-nosed bats | Hipposideros | entipat |
| Leaf-nosed bats | Hipposideros sp.? |  |
| Slit-faced bats | Nycteridae | entipat |
| Slit-faced bats | Nycteris sp.? |  |
| Sheath-tailed bats, | Emballonuridae | entipat |
| African sheath-tailed bats | Coleura afra? |  |
| Tomb bats | Taphozous sp.? |  |
| Free-tailed bats | Molossidae | entipat |
| Guano bats | Tadarida sp.? |  |
| Wrinkle-lipped bats | Chaerophon? |  |
| Mop’s free-tailed bats | Mops sp.? |  |
| Giant mastiff bat | Otomops martiensseni? |  |
| Long-fingered bats | Miniopteridae |  |
| Long-fingered bats, | Miniopterus sp.? |  |
| Vesper bats | Vespertillonidae | entipat |
| Hairy bats | Myotis sp.? |  |
| Woolly bats | Kerivoula sp.? |  |
| House bats | Scotophilus sp.? |  |
| Butterfly bats | Glauconycteris sp.? |  |
| Moloney’s flat-headed bat | Mimetillus moloneyi? |  |
| Sclieffen’s twilight bat | Nyctecuys schliefferi |  |
| Pipistrelles | Pipistrellus sp.? |  |
| Carnivores | Carnivora |  |
| Dogs | Canidae |  |
| African wild dog | Canis/Lycaon pictus | suyian |
| Black-backed jackal * | Canis mesomelas schmidti | embarie |
| Bat-eared fox | Otocyon megalotis virgatus | esiro |
| Mustelids | Mustelidae |  |
| Zorilla | Ictonyx striatus |  |
| Ratel/honey badger * | Melivora capensis | onkoirish |
| Otters | Lutrinae |  |
| African clawless otter | Aonyx capensis? |  |
| Cats | Felidae |  |
| Leopard * | Panthera pardus | olowuaru keri |
| Cheetah | Acinonyx jubatus | olnyarra |
| Lion | Panthera leo | Orng"atuny |
| Serval | Leptailurus serval | orkushee |
| Caracal | Caracal caracal | enchulugo |
| Wildcat | Felis sylvestris | empuus entim |
| Viverrids | Viverridae |  |
| African Civet * | Civettictis cicetta | orkushee |
| Common genet | Genetta genetta |  |
| Blotched genet | Genetta maculata |  |
| Hyenas | Hyaenidae |  |
| Striped hyena * | Hyaena hyaena | orkonoi |
| Spotted hyena * | Crocuta crocuta | orkonoi |
| Aardwolf | Proteles cristata septentrionalis | oldia lentim |
| Mongooses | Herpestidae | osiooj |
| White-tailed mongoose | Ichneumia albicauda |  |
| Echneumon/Egyptian Mongoose | Herpestes ichneumon |  |
| Slender mongoose | Herpestes sanguineus |  |
| Bushy-tailed mongoose | Bdeogale crassicauda |  |
| Banded mongoose * | Mungos mungo |  |
| Dwarf mongoose * | Helogale parvula |  |
| Somali dwarf mongoose | Helogale hirtula |  |
| Pangolins | Pholidota |  |
|  | Manidae |  |
| Ground pangolin | Smutsia temminckii |  |
| Odd-toed ungulates | Perissodactyla |  |
| Equids | Equidae |  |
| Common zebra * | Equus quagga boehmi | oloitiko |
| Grevy’s zebra * | Equus grevyi | orkanka |
| Rhinoceros | Rhinocerotidae |  |
| White rhinoceros * | Ceratotherium simium | emuny |
| Even-toed ungulates | Cetartiodactyla |  |
| Pigs | Suidae |  |
| Bushpig | Potamochoerus larvatus | orguyia |
| Common warthog * | Phacochoerus africanus? | orbitir |
| Desert warthog | Phacochoerus aethiopicus? | orbitir |
| Giraffes | Giraffidae |  |
| Reticulated giraffe * | Giraffa camelopardis reticulata | ormara\loodo orgos |
| Spiral-horned bovines | Tragelaphini |  |
| Lesser kudu * | Tragelaphus imberbis | ormaalo |
| Greater kudu * | Tragelaphus strepsiceros | ormaalo |
| Bushbuck * | Tragelaphus scriptus | orkuaa |
| Common eland * | Taurotragus oryx | osirua |
| Antelopes | Antilopinae |  |
| Duikers | Cephalophini |  |
| Bush duiker | Sylvicapra grimmia | ologol |
|  |  | ologol |
| Dikdiks | Madoquini |  |
| Günther’s dikdik | Madoqua guentheri | eronko |
| Kirk’s dikdik * | Madoqua kirkii kirkii + Madoqua kirkii cavendishi |  |
| Gazelline antelopes | Antilopini |  |
| Thomson’s gazelle * | Eudorcas thomsoni? |  |
| Tana gazelle | Nanger granti petersi | nasira marae |
| Bright’s gazelle | Nanger granti notata ? |  |
| Gerenuk | Litocanus walleri |  |
| Reduncines and kobs | Reduncini |  |
| Waterbuck, Kobus * ellipsiprymnus ellipsiprymnus + Kobus ellipsiprymnus defassa |  | kuroo |
| Klipspringer | Oreotragini |  |
| Klipspringer * | Oreotragus oreotragus | enkisil |
| Impala | Aepycerotini |  |
| Impala * | Aepyceros melampus melampus | naibor kurum |
| Horse-like antelopes | Hippotragini |  |
| Beisa oryx | Oryx beisa beisa | olchurua |
| Bovids | Bovidae |  |
| Buffalo | Syncerus caffer | olarross |

Birds of Il Ngwesi

Order:   Pelacaniformes

Family:  	Herons                                           	Ardeidae

Little egret                                                    	Egretta garzetta

Grey heron                                                   	Ardea cinerea

Family:  	Hamerkops                                   	Scopidae

Hamerkop                                                     	Scopus umbretta

Order:   Ciconiiformes

Family:  	Storks                                            	Ciconidae

White stork                                                  	Ciconia ciconia

Family:  	Ibises                                             	Threskiornithidae

Hadada ibis                                                   	Bostrychia hagedash

Order:   Anseriformes

Family:  	Watefowl                                      	Anatidae

Egyptian goose                                           	Alopochen aegyptiaca

Order:   Accipitriformes

Family:  	Secretary birds                             	Sagittariidae

Secretary bird                                              	Sagittarius serpentarius

Family:  	Eagles, Hawks, Kites etc.              	Accipitridae

Kites:

Black kite                                                       	Milvus migrans

Black-winged kite                                       	Elanus caeruleus

Fish-eating raptors:

African fish eagle                                        	Haliaeetus vocifer

Solitary vultures:

Hooded vulture                                          	Necrosyrtes monachus

White-backed vulture                              	Gyps africanus

Rüppell's vulture                                        	Gyps rueppellii

Lappet -faced vulture                               	Torgos tracheliotos

Snake eagles:

Black-chested snake eagle                     	Circaetus pectoralis

Brown snake eagle                                    	Circaetus cinereus

Harriers:

African marsh harrier                                	Circus ranivorus

Chanting goshawks:

Eastern chanting goshawk                      	Melierax poliopterus

Gabar  goshawk                                          	Micronisus gabar

Hawks:

African harrier-hawk                                	Polyboroides typus

Grasshopper buzzard                               	Butastur rufipennis

Typical buzzards:

Augur buzzard                                             	Buteo augur

Large brown eagles:

Tawny eagle                                                 	Aquila rapax

Steppe eagle                                                	Aquila nipalensis

Lesser spotted eagle                                 	Clanga pomarina

Hawk-eagles:

Booted eagle                                               	Hieraaetus pennatus

African hawk-eagle                                   	Aquila spilogaster

Atypical eagles:

Bateleur                                                         	Terathopius ecaudatus

Long-crested eagle                                    	Lophaetus occipitalis

Large eagles:

Verreaux's eagle                                        	Aquila verreauxii

Martial eagle                                               	Polemaetus bellicosus

Crowned eagle                                            	Stephanoaetus coronatus

Order:   Falconiformes

Family:  	Falcons                                          	Falconidae

Brown kestrels:

Common kestrel                                         	Falco tinnunculus

Lesser kestrel                                              	Falco naumanni

Falcons:

African pygmy falcon                                	Polihierax semitorquatus

Bat hawk                                                       	Macheiramphus alcinus

Large falcons:

Lanner falcon                                               	Falco biarmicus

Order:   Galliformes

Family:  	Guineafowls                                  	Numididae

Helmeted guineafowl                              	Numida meleagris

Vulturine guineafowl                                	Acryllium vulturinum

Family:  	Pheasants and partridges            	Phasianidae

Francolins and patridges:

Scaly spurfowl                                             	Pternistis squamatus

Stone partridge                                           	Ptilopachus petrosus

Crested francolins:

Yellow-necked spurfowl                          	Pternistis leucoscepus

Crested francolin                                        	Ortygornis sephaena

Quails:

Common quail                                             	Coturnix coturnix

Order:   Gruiformes

Family:  	Cranes                                           	Gruidae

Gray-crowned crane                                 	Balearica regulorum

Order:   Otidiformes

Family:  	Bustards                                        	Otididae

Large bustards:

Kori bustard                                                 	Ardeotis kori

Small bustards:

Buff-crested bustard                                	Lophotis gindiana

Black-bellied bustard                                	Lissotis melanogaster

Order:   Charadriiformes

Family:  	Stone curlews                               	Burhinidae

Spotted thick-knee                                   	Burhinus capensis

Family:  	Pratincoles and coursers             	Glareolidae

Double-banded courser                          	Rhinoptilus africanus

Three-banded courser                             	Rhinoptilus cinctus

Family:  	Plovers, dotterels, and lapwings 	Charadriidae

Blacksmith lapwing                                    	Vanellus armatus

Crowned lapwing                                       	Vanellus coronatus

Blacked-winged lapwing                         	Vanellus melanopterus

Family:  	Sandpipers                                    	Scolopacidae

Common sandpiper                                  	Actitis hypoleucos

Family:  	Sandgrouse                                   	Pteroclidae

Black-faced sandgrouse                          	Pterocles decoratus

Chestnut -bellied sandgrouse               	Pterocles exustus

Order:   Columbiformes

Family:  	Pigeons and doves                       	Columbidae

Speckled pigeon                                         	Columba guinea

Emerald-spotted wood dove                	Turtur chalcospilos

Namaqua dove                                           	Oena capensis

Ring-necked dove                                      	Streptopelia capicola

Red-eyed dove                                           	Streptopelia semitorquata

Mourning collared dove                          	Streptopelia decipiens

Laughing dove                                             	Spilopelia senegalensis

Order:   Psittaciformes

Family:  	Holotropical parrots                    	Psittacidae

African orange-bellied parrot                	Poicephalus rufiventris

Family:  	Old World parrots                        	Psittaculidae

Fischer's lovebird                                       	Agapornis fischeri

Order:   Musophagiformes

Family:  	Turacos                                         	Musophagidae

Hartlaub's turaco                                        	Tauraco hartlaubi

White-bellied go-away-bird                   	Corythaixoides leucogaster

Order:   Cuculiformes

Family:  	Cuckoos                                        	Cuculidae

Crested cuckoos:

Great-spotted cuckoo                              	Clamator glandarius

Jacobin cuckoo                                            	Clamator jacobinus

Grey cuckoos:

African cuckoo                                            	Cuculus gularis

Common cuckoo                                        	Cuculus canorus

Dark and long -tailed cuckoos

Red-chested cuckoo                                 	Cuculus solitarius

Black cuckoo                                                	Cuculus clamosus

Shinning cuckoos and yellowbills:

Klaa's cuckoo                                               	Chrysococcyx klaas

African emerald cuckoo                           	Chrysococcyx cupreus

Coucals:

White-browed coucal                               	Centropus superciliosus

Order:   Strigiformes

Family:  	Owls                                              	Strigidae

Owls:

African scops owl                                       	Otus senegalensis

Verreaux's eagle-owl                                	Bubo lacteus

Spotted eagle-owl                                     	Bubo africanus

Owlets :

Pearl-spotted owlet                                  	Glaucidium perlatum

Order:   Caprimulgiformes

Family:  	Nightjars                                       	Caprimulgidae

Slender-tailed nightjar                             	Caprimulgus clarus

Sombre nightjar                                          	Caprimulgus fraenatus

European nightjar                                      	Caprimulgus europaeus

Order:   Apodiformes

Family:  	Swifts                                            	Apodidae

Little swift                                                     	Apus affinis

Common swift                                             	Apus apus

Order:   Coliiformes

Family:  	Mousebirds                                   	Coliidae

Blue-naped mousebird                            	Urocolius macrourus

Speckled mousebird                                 	Colius striatus

White-headed mousebird                      	Colius leucocephalus

Order:   Trogoniformes

Family:  	Trogons                                         	Trogonidae

Narina trogon                                              	Apaloderma narina

Order:   Coraciiformes

Family:  	Kingfishers                                    	Alcedinidae

Grey-headed kingfisher                           	Halcyon leucocephala

Family:  	Bee-eaters                                     	Meropidae

Little bee-eater                                          	Merops pusillus

Cinnamon-chested bee-eater               	Merops oreobates

European bee-eater                                 	Merops apiaster

Family:  	Rollers                                           	Coraciidae

Lilac-breasted roller                                  	Coracias caudatus

European roller                                           	Coracias garrulus

Purple roller                                                 	Coracias naevius

Family:  	Wood hoopoes                             	Phoeniculidae

Green wood hoopoe                                	Phoeniculus purpureus

Common scimitarbill                                 	Rhinopomastus cyanomelas

Family:  	Hoopoes                                        	Upupidae

African hoopoe                                           	Upupa africana

Family:  	Hornbills                                       	Bucerotidae

Eastern yellow-billed hornbill                	Tockus flavirostris

Jackson's hornbill                                       	Tockus jacksoni

Von der decken's hornbill                       	Tockus deckeni

Red-billed hornbill                                     	Tockus erythrorhynchus

African grey hornbill                                  	Tockus nasutus

Order:   Piciformes

Family:  	Bush tinkerbirds & barbets          	Lybiidae

Red-fronted tinkerbird                            	Pogoniulus pusillus

Red-fronted barbet                                   	Tricholaema diademata

Red and yellow barbet                             	Trachyphonus erythrocephalus

D'arnaud's barbet                                      	Trachyphonus darnaudii

Family:  	Honeyguides                                 	Indicatoridae

Greater honeyguide                                 	Indicator indicator

Lesser honeyguide                                    	Indicator minor

Family:  	Woodpeckers                               	Picidae

Nubian woodpecker                                 	Campethera nubica

Cardinal woodpecker                               	Dendropicos fuscescens

Order:   Passeriformes

Family:  	Larks                                              	Alaudidae

Rufous-naped lark                                     	Mirafra africana

Red-winged lark                                         	Mirafra hypermetra

Pink-breasted lark                                     	Calendulauda poecilosterna

Family:  	Swallows                                       	Hirudinidae

Lesser striped swallow                             	Cecropis abyssinica

Mosque swallow                                        	Cecropis senegalensis

Family:  	Wagtails & pipits                          	Motacillidae

African pied wagtail                                   	Motacilla aguimp

African pipit                                                  	Anthus cinnamomeus

Red-throated pipit                                     	Anthus cervinus

Family:  	Cuckooshirikes                             	Campephagidae

Black cuckooshrike                                    	Campephaga flava

Red-shouldered cuckooshrike              	Campephaga phoenicea

Grey cuckooshrike                                     	Coracina caesia

Family:  	Bulbuls                                          	Pycnonotidae

Common bulbul                                          	Pycnonotus barbatus

Yellow-vented bulbul                               	Pycnonotus tricolor

Family:  	Old World flycatchers                  	Muscicapidae

Robins:

White-browed robin-chat                      	Cossypha heuglini

Red-capped robin-chat                            	Cossypha natalensis

White-winged scrub-robin                     	Cercotrichas leucophrys

Thrushes:

Spotted morning-thrush                         	Cichladusa guttata

Ruffus-tailed rock thrush                        	Monticola saxatilis

Flycatchers:

African grey flycatcher                             	Bradornis microrhynchus

Family:  	Cisticolas                                       	Cisticolidae

Croaking cisticola                                        	Cisticola natalensis

Pale prinia                                                     	Prinia somalica

Grey-backed camaroptera                     	Camaroptera brevicaudata

Yellow-breasted apalis                             	Apalis flavida

Insects of Il Ngwesi

Insects have not yet been identified down to species level. However, most of the insects we observed during Phase 1 have been categorised at least down to order level:

- Lepidoptera (butterflies and moths)

- Diptera (true flies)

- Neuroptera (lacewings, mantidflies, antlions)

- Hymenoptera (ants, bees, wasps, sawflies)

- Coleoptera (beetles)

- Blattodea (termites and cockroaches)

- Hemiptera (true bugs)

- Orthoptera (grasshoppers, locusts, crickets)

- Phasmatodea (stick insects)

- Mantodea (mantises)

Other Arthropods:

- Araneae (spiders)

- Scorpiones (scorpions)

- Pseudoscorpiones (pseudoscorpions)

- Spirostreptida (millipedes)

Grass List of Il Ngwesi

This grass list is based on observations made during the reconnaissance trip. Some species are seasonal, so would not have been observed during the dry season when the reconnaissance was carried out.

| Common name | Latin name |
| --- | --- |
| Elephant grass | Panic umeona maximum |
| Rabbit foot grass | Polypogon monspeloensis |
| Elegant three-awn grass | Aristida adoensis |
| Bush grass | Calamagrostis epigejos |
| Buffel grass | Cenchrus ciliaris |
| Feather -top chloris | Chloris virgata |
| Sickle grass | Ctenium concinnum |
| Star grass | Cynodon nlemfuensis |
| Common crowfoot grass | Dactyloctenium aegyptium |
| Small crowfoot grass | Dactyloctenium geminatum |
| Finger millet | Eleusine coracana |
| Needle grass | Enteropogon macrostachyus |
| Feather love grass | Eragrostis amabilis |
| Woolly love grass | Eragrostis ciliaris |
| Button love grass | Eragrostis exasperata |
| Streamside love grass | Eragrostis namaquensis |
| Dryland love grass | Eragrostis racemosa |
| Curly -leaf love grass | Eragrostis rigidior |
| Dwarf love grass | Eragrostis sennii |
| Saw-toothed love grass | Eragrostis superba |
| Weedy love grass | Eragrostis tenuifolia |
| Short spear grass | Harpachne schimperi |
| Tall spear grass | Heteropogon contortus |
| Red top grass | Melinis repens |
| Small guinea grass | Panicum coloratum |
| Hairy guinea grass | Panicum deustum |
| Carrot-seed grass | Tragus berteronianus |
| Annual bristle grass | Aristida adscensionis |
| Herringbone grass | Pogonarthria squarrosa |
| Golden bristle grass | Setaria sphacelata |
| Bur-bristle grass | Setaria verticillata |

Appendix 5: Laikipiak Maa Glossary

Please find below the glossary the team has compiled during their time at Il Ngwesi, learning various words relevant to life during the mission!

Greetings

Supa- hello

Supa oleng – response to supa – I am fine

Ira supat? – How are you?

Kara supat – I am fine

Kejaa? Hi/how are you?

Kesidai – Beautiful

Kejaa seran inno- good morning (how was your morning?)

Ole sere- see you later

Ekidua - see you later (alternative)

Basic words and phrases

Nanu - me

Iyie- you

Ninye- he/she/it

Yioo- we

Intae- y'all

Ninche- they

Kara - I am

Ira- you are

Kera- he/she/it is

Ekira- we are

Irara- yall are

Kera ninche- they are

O - and

anaa - or

E – of

Ata nanu- me too

Kumok- many

Sidai oleng- so nice

Nyoo- what

Ng'ae- who

Anu- when

Ainyo- why

Aikaja- how

Ekaiyiolo – I know

Maiyiolo- I don't know

Ang – home/mine/ours

Ekira enjori – we are a team

Entito- girl

Laiyoni- boy

Kerai- child

Enkerai- baby

Moratai- age mate

Nakerai – baby – when speaking to your beloved

Engari – car

Enkijabe- cold

Kerewa- joto-hot

Loipi = shade

Oltaa -light

Emwangan - brightness

Enkolon- sun

Nashipai  - happy

Enkini - small

Esapuk - bit

Sapok- big

Abori teindie - down there

Dukuya- ahead

Tenebo - together

Kanyor = I like/love

Kaiba  - I don't like/love

Numbers

Obo - 1

Keti osiruwa obo  - there is 1 eland

Wa'are  - 2

Okuni - 3

O'ongwan - 4

Imiyiet - 5

Ile - 6

Sapa /na'apishana – 7

Isiet - 8

Naodo - 9

Tomon  - 10

Tikitam - 20

Tomo uni - 30

Animals

Enketeng- cow

Enkichu- cattle

Nkimeji- goat

Nkerra- sheep

Nturkulu - dove

Osiruwa- eland

Osiruwai - elands

Loitiko- common zebra

Orkanka- Grevy’s zebra

Loibor korrom  - white bum (also Grevy’s zebra)

Sidai- beautiful/ostrich

Nyara - duma- cheetah

Suyian – wild dog

Enaishiridama- aardvark

Oloikuma- pancake tortoise

Osaikeri- Eagle

Esampuripuri- butterfly

Oltome- elephant

Iltomiyia- elephants

Oldere - vervet monkey

Olotim- baboon

Lodo ogus-long neck (giraffe)

Olotoroi- bee

Okuroo- waterbuck

Oltilo- woodpecker

Rkimong- Bush baby

Centipede - enkuloba

Scorpion - endengkel

Spider - kedi

Oiyai- porcupine

Embarie- bat eared fox

Emuny - rhino

Enkirokwe  - yellow vented bulbul/ Black headed bulbul

Oromoinko- kudu

Enkoirish- honey badger

Emuny- rhino

Emuny narok- black rhino

Emuny naibor- white rhino

Plants

Oromariko- banana

Oserai /orpopongi- tree euphorbia

Olongororeki - tall spear grass

Irkeek- firewood

Lemurran - mint ( plant for warriors)

Sukurrtuti - creeper

Food and drink

Enkare- water

Kishamu oleng – very tasty/delicious/sweet

Kolenaoto- yoghurt (sour milk)

Kole – milk

Naoto- sour

Irnga'ayu- fruits

Oromaiyai / oromosori- eggs

Breakfast - enndaa enteseran

Lunch - endama

Dinner- enndaa enteipa

Enndaa- food

Kemelok - delicious

Monono - goat blood, fat and neck meat cooked together – a Maasai delicacy only for men

Verbs

Kaiyieu  - I want

Maiyieu - I don't want

Iyieu- you want

Miyieu  - you don't want

Keiyieu- he/she/it wants

Meiyieu- he/she/it doesn't want

Ekiyieu- we want

Mekiyieu- we don't want

Iyieuu - yall want

Miyieuu- yall don't want

Keyieu- they want

Meyieu - they don't want

Kaidim- I can

Maidim - I can't

Indim- you can

Mindim- you cant

I want to go- kaiyieunalo

Kaloito  - I go

Kaloito ang- I’m going home

Ekipoito- we are going

I see  - kadolita

Madolita  - I don't see

Kayieu- to want

Kadol- to see

Kadolita- I see

Ainyang'u- to buy

Amir- to sell

Alo- to go

Alotu- to come

Ashukunye- to return

Akwet- to run

Aning- to hear

Keti- there is

Meti- there is not

Keidimayu netii- there might be

Ainos- to eat

Aok- to drink

Maape ainos endaa- let's go eat food

Airura- to sleep

Maape airura- let's go sleep

Ainyooto- to wake up

Airritisho - to graze animals

Ashuku- to return animals at night

Atoningo- i hear

Etoningo- he/she/they hear

Itiningo- you hear

Kitabautua- we have arrived

Aitiemo- I'm full

Misc.

Lalak - tooth

Olalai- teeth

Olalem- sword

Sain- shanga beads

Loibor- white

Korrom - bum/back

Osiwe olo - moving winds

Osenyiai- sand

Olobor  - the calm one

Ogulkwe  - hard headed/naughty

Oltome ogulkwe - naughty elephant

Kegol ninche nkweishi- hard them heads

Enkwe - head

Oltamoloji- dead leg

# Bibliography

# Books

# Stevenson, T; Fanshawe, J; Small, B 2020, Field Guide to the Birds of East Africa: Kenya, Tanzania, Uganda, Rwanda, Burundi, Helm

Kingdon, J 2019, The Kingdon Guide to African Mammals Bloomsbury

Martins, D 2015, Insects of East Africa, Penguin Random House South Africa

Martins, D 2022, Grasses of East Africa, Penguin Random House South Africa

Journal Articles

Bibby, C.J. (2004) ‘Bird diversity survey methods’, Bird Ecology and Conservation, pp. 1–16. doi:10.1093/acprof:oso/9780198520863.003.0001.

Ireri, P., Kung’u, J. and Muriithi, J. (2020) ‘Distribution of the benefits of Ngare Ndare Forest Trust and il ngwesi group ranch ecotourism enterprises in Kenya’, December 2020, (9(5)), pp. 1178–1192. doi:10.46222/ajhtl.19770720-76.

Landmann, T. et al. (2023) ‘Insect diversity is a good indicator of biodiversity status in Africa’, Nature, 4(1). doi:10.1038/s43247-023-00896-1.

Magagula, C.N. (2022) ‘Rapid assessment of ant (Formicidae) and beetle (Carabidae, Scarabaeidae, Tenebrionidae) assemblages across an ecological gradient in an African savanna for conservation planning’, Proceedings of the Zoological Society, 75(2), pp. 221–230. doi:10.1007/s12595-022-00432-7.

Nyingi, D.W., Gichuki, N. and Ogada, M.O. (2013) ‘Freshwater ecology of Kenyan highlands and Lowlands’, Developments in Earth Surface Processes, pp. 199–218. doi:10.1016/b978-0-444-59559-1.00016-5.

Oindo, B.O., De By, R.A. and Skidmore, A.K. (2001) ‘Environmental factors influencing bird species diversity in Kenya’, African Journal of Ecology, 39(3), pp. 295–302. doi:10.1046/j.1365-2028.2001.00322.x.

Simonson, W.D., Allen, H.D. and Coomes, D.A. (2014) ‘Applications of airborne lidar for the assessment of Animal Species Diversity’, Methods in Ecology and Evolution, 5(8), pp. 719–729. doi:10.1111/2041-210x.12219.

Thomas, N. and Brooks, S. (2004) ‘Ecotourism for Community Development: Environmental Parnerships and the il ngwesi ecotourism project, Northern Kenya’, Africa Insight, 33(1). doi:10.4314/ai.v33i1.22304.

Websites

Il Ngwesi Community Conservancy: ilngwesi.com

Northern Rangelands Trust: nrt-kenya.org

Lewa Wildlife Conservancy: lewa.org

Mpala Research Centre: mpala.org

World Agroforestry Institute: worldagroforestry.org

Natural State: naturalstate.org

African Butterfly Research Institute: https://www.lepsocafrica.org/?p=activities&s=regions

National Museums of Kenya: museums.or.ke

Other Resources:

LDSF Field Manual:

https://worldagroforestry.org/output/land-degradation-surveillance-framework-field-manual

# Acknowledgements

We thank the following organisations and individuals for their invaluable help with this project:

Advisors:

Dr Dino Martins, Director of the Turkana Basin Research Institute

Zoë Simmons, Head of Life Collections for the University of Oxford Museum of Natural History

Steve Collins, Director of the African Butterfly Research Institute

Dr Rebecca Senior of Durham University

Dr Kieren Avery of Native

Professor Robert Baxter and Professor Dave Roberts of Durham University

Dr Tor-Gunnar Vågen and Dr Leigh Winowiecki of World Agroforestry

John Tanui of Lewa Wildlife Conservancy

Ian Craig founding member of the Northen Rangelands Trust

Jonathan Baillie, Catherine Machungo and the field research team of Natural State

Partners:

Nigel Winser, Elder of Il Ngwesi Conservancy, organiser of the annual Oman Natural Heritage Annual Lectures 2016-2024 and old executive vice president of Earthwatch.

Dominic Karmushu, Board member for Il Ngwesi

Kip Ole Polos, Chairman of Il Ngwesi and LCA (Laikipia conservancy association)

Dr Mohammad Shibia of the Northern Rangelands Trust

Edwin Kisio, Conservation Manager for Il Ngwesi

The Lodge Staff of Il Ngwesi for their tremendous warmth and hospitality

Doners:

Durham University Expedition grant – with thanks to Professor Robert Baxter and Professor Dave Roberts

St Cross College – with special thanks to Dr Joanna Ashbourn

# Key contacts and address in Kenya and UK

Edwin Kisio: edwinkisio2021@gmail.com

Cyrus Kisio: cyruskisio@gmail.com

Francis McAdie: Francis@redmcadie.com

Benjamin Ngila: benngila7@gmail.com

Barbara Francik: barbara.francik@pmb.ox.ac.uk

Everlyne Masikonte: evamnyange@gmail.com

Eva Rundle: eva.rundle@gmail.com

Robin Tentuan: rabintent@gmail.com

Jamie Bolam: jamiebolam@protonmail.com